# ORE SOP 002

# Procedure to Request a No-Cost Extension

While sponsors expect Principal Investigators (PI) to complete projects by the stipulated end date, occasionally, extra time is needed.  A no-cost extension gives the PI extra time to complete the scope and objectives of the project without additional funds being provided by the sponsor.  Although requests may not be made for the sole purpose of spending remaining funds, you may expend remaining funds during the no-cost extension period.

Prior sponsor approval is required in order to grant additional time to complete projects.  Most sponsors require an official request from the Authorized Organizational Representative of the awardee institution, the R&D Center Director for UPRM.  Requests for no cost extensions must be made in accordance to the terms and conditions of the award, but in general, the process is as follows:

- The PI/PD identifies the need of extra time to accomplish the scope and objectives of his project and contacts the R&D Center Director or the Pre-Award Office for guidance.

- The PI/PD must state in writing the reasons for requesting the No-Cost Extension, either in form of a letter addressed to the Program Officer or electronically making the request at the sponsor’s award management website (NSF FastLane, NOAA Grants Online, NIH eRA Commons).

  - In the case of a written letter, the Request for No-Cost Extension letter is signed by the R&D Center Director and the PI, and mailed or emailed to the sponsor.

  - For requests to sponsors with award management websites, the PI initiates the Notification of No-Cost Extension Request and it is submitted to the sponsor by the Authorized Organizational Representative, the R&D Center Director, in coordination with the Pre-Award Office and the Post-Award Administrator.

- Sponsor approval response is required in order to extend the project period.  The sponsor’s official communication is shared with the PI, and the R&D Center Budget Office, to implement the appropriate date changes in the financial systems.