Cooperative Agreement

Quarterly Progress Report

| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |  |
| --- | --- |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |  |
| Agreement Number: 68-F352-17-182 |  |
| Project Director: Dr. Myrna Comas myrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information: Roberto Rigau robertoluis.rigaullorens@upr.edu | Phone (787)765-8000 |
| Period Cover by Report: 01/01/2019-03/31/2019 |  |
| Project End Date: August 1, 2020 |  |
| - General Progress Report - Staff meeting to follow up project works. - Technical meeting - Individual and staff meetings were conducted with professor that worked with Crops for High Tunnel Guide and Community Organization Guide. Every one continue to collect data for the publications. - Farmer’s technical assistance - Visit 10 farmers to begin the outreach process. - Development of Community Gardens Curriculum it’s ready to print final draft to present to USDA NRCS for its approval. - Present PR Agribusiness Development Plan Guide “Planificando Mi Finca” to USDA NRCS for its approval. |  |
| - Comparison of Actual and Proposed Accomplishments - Incorporated more material to PAU web page - We have a delay on Development of Community Gardens Curriculum and PR Agribusiness Development Plan Guide, but know we waited for USDA NRCS approval to print final copies - We continue offering technical assistance to small farmers on NRCS high tunnel assistance program. - We work on high tunnel poster design. - We work on Crops for High Tunnel Guide and Community Organization Guide - We began to work on electronic business plan. |  |
| - Describe the work that you anticipate completing in the next six month - Met with Farm Service Agency personnel to incorporate on PAU - Finish High Tunnels Poster Design and Printing - Development of Community Gardens Curriculum Print - PR Agribusiness Development Plan Guide Print - High Tunnel Development Plan for Farmers Print - Create Electronic High Tunnel Development Plan for farmers |  |