Cooperative Agreement

Quarterly Progress Report

| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |  |
| --- | --- |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |  |
| Agreement Number: 68-F352-17-182 |  |
| Project Director: Dr. Myrna Comas myrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information: Roberto Rigau robertoluis.rigaullorens@upr.edu | Phone (787)765-8000 |
| Period Cover by Report: 07/01/2018-09/30/2018 |  |
| Project End Date: August 1, 2020 |  |
| - General Progress Report - Continue with coordination work with PRAES Administrative Office - Technical meeting - Individual meetings were conducted with professor that worked with Community Gardens Curriculum, Crops for High Tunnel Guide and Community Organization Guide. Every one continue to collect data for their publications. - PAU web page - Acquire permission to use Word Press to develop the page, met with the student programmer to define the content of the page - Farmer’s technical assistance - Visit 10 farmers to begin the outreach process. We developed a farmer’s project records to collect data about their project status |  |
| - Comparison of Actual and Proposed Accomplishments - We were no able to accomplish any of our objectives, since we are only few month into the project. Therefore, we continue to collect data for curriculum guides and general guides. - PRAES Human Resources Documents were completed - We continue with the process to acquire computational device and finish with expendable material acquisition. - A student programmer was recruited and get permission to use Word Press to develop PAU web page. - We began offering technical assistance to small farmers on NRCS high tunnel assistance program. |  |
| - Describe the work that you anticipate completing in the next six month - Travel to Cleveland Ohio - High Tunnels Poster Design and Printing - Development of Community Gardens Curriculum - PR Agribusiness Development Plan Guide - High Tunnel Development Plan for farmers |  |