**Cooperative Agreement**

**Quarterly Progress Report**

|  |
| --- |
| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |
| Agreement Number: 68-F352-17-182 |
| Project Director: Dr. Myrna Comasmyrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information:Roberto Rigaurobertoluis.rigaullorens@upr.edu | Phone(787)765-8000 |
| Period Cover by Report: 10/01/2019-12/31/2019 |
| Project End Date: August 1, 2020 |
| 1. General Progress Report
2. Staff meeting to follow up on project works.
3. Development of Community Gardens Curriculum, pending to print in PRAES Print Office
4. Present Urban Agriculture Tool Kit and Agricultural Community Organization Guide to review and design in PRAES Print Office
5. Promoted Urban Agriculture project in WPAB Radio Station - Ponce and in “Desde la EEA” PodCast – Rio Piedras
6. Met with San Juan chef to identify agricultural products alternative for High Tunnel Producers
 |
| 1. Comparison of Actual and Proposed Accomplishments
* We had a delay in Community Gardens Curriculum Guide, know is pending to print in PRAES printing office
* The Urban Agriculture Tool Kit and Community Organization Guide were presented to PRAES Print Office for their review and recommendations.
* We continue working on Crops for High Tunnel Guide
 |
| 1. Describe the work that you anticipate completing in the next six month
* Print and present training of Community Gardens Curriculum, Urban Agriculture Tool Kit, Agricultural Community Organization Guide and Crops for High Tunnel Guide
* Coordinate forum to promote marketing net between High Tunnel Producers and Supply Chain Members
 |