Cooperative Agreement

Quarterly Progress Report

| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |  |
| --- | --- |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |  |
| Agreement Number: 68-F352-17-182 |  |
| Project Director: Dr. Myrna Comas myrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information: Roberto Rigau robertoluis.rigaullorens@upr.edu | Phone (787)765-8000 |
| Period Cover by Report: 10/01/2019-12/31/2019 |  |
| Project End Date: August 1, 2020 |  |
| - General Progress Report - Staff meeting to follow up on project works. - Development of Community Gardens Curriculum, pending to print in PRAES Print Office - Present Urban Agriculture Tool Kit and Agricultural Community Organization Guide to review and design in PRAES Print Office - Promoted Urban Agriculture project in WPAB Radio Station - Ponce and in “Desde la EEA” PodCast – Rio Piedras - Met with San Juan chef to identify agricultural products alternative for High Tunnel Producers |  |
| - Comparison of Actual and Proposed Accomplishments - We had a delay in Community Gardens Curriculum Guide, know is pending to print in PRAES printing office - The Urban Agriculture Tool Kit and Community Organization Guide were presented to PRAES Print Office for their review and recommendations. - We continue working on Crops for High Tunnel Guide |  |
| - Describe the work that you anticipate completing in the next six month - Print and present training of Community Gardens Curriculum, Urban Agriculture Tool Kit, Agricultural Community Organization Guide and Crops for High Tunnel Guide - Coordinate forum to promote marketing net between High Tunnel Producers and Supply Chain Members |  |