**Cooperative Agreement**

**Quarterly Progress Report**

|  |
| --- |
| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |
| Agreement Number: 68-F352-17-182 |
| Project Director: Dr. Myrna Comasmyrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information:Roberto Rigaurobertoluis.rigaullorens@upr.edu | Phone(787)765-8000 |
| Period Cover by Report: 10/01/2018-12/31/2018 |
| Project End Date: August 1, 2020 |
| 1. General Progress Report
2. Technical meeting - Individual meetings were conducted with professor that worked with Crops for High Tunnel Guide and Community Organization Guide. Every one continue to collect data for their publications.
3. Created PAU web page
4. Farmer’s technical assistance - Visit 3 farmers to begin the outreach process.
5. Participated on Ohio’s Cleveland Seasonal High Tunnel Project Workshop, Cleveland Ohio
6. Present Development of Community Gardens Curriculum to PRAES Educational Media and Information Office
7. Present PR Agribusiness Development Plan Guide to PRAES Educational Media and Information Office
 |
| 1. Comparison of Actual and Proposed Accomplishments
* Created PAU web page
* We finished the process to acquire computational device.
* We continue offering technical assistance to small farmers on NRCS high tunnel assistance program.
* We work on high tunnel poster design.
* We edited Development of Community Gardens Curriculum and PR Agribusiness Development Plan Guide.
 |
| 1. Describe the work that you anticipate completing in the next six month
* Met with Farm Service Agency personnel to incorporate on PAU
* Finish High Tunnels Poster Design and Printing
* Development of Community Gardens Curriculum Print
* PR Agribusiness Development Plan Guide Print
* High Tunnel Development Plan for Farmers Print
* Create Electronic High Tunnel Development Plan for farmers
 |