**Cooperative Agreement**

**Quarterly Progress Report**

|  |
| --- |
| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |
| Agreement Number: 68-F352-17-182 |
| Project Director: Dr. Myrna Comasmyrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information:Roberto Rigaurobertoluis.rigaullorens@upr.edu | Phone(787)765-8000 |
| Period Cover by Report: 01/01/2020-03/31/2020 |
| Project End Date: August 1, 2020 |
| 1. General Progress Report
2. Staff meeting to follow up on project works.
3. Present Project on “Asociación de Profesores del Recinto Universitario de Mayagüez” Radio Program on WKJB Radio Station
4. Present project on NRCS State Technical Committee Meeting.
5. Printing of Community Gardens Curriculum and Urban Agriculture Tool Kit pending to approve by the Puerto Rico State Commission on Elections (PRSCE)
6. Development of Agricultural Community Organization Guide was presented to review and design in PRAES Print Office
7. Began to write High Tunnel Management and Production Guide
 |
| 1. Comparison of Actual and Proposed Accomplishments
* We had a delay in Community Gardens Curriculum Guide and Urban Agriculture Tool Kit, know is pending of PRSCE
* The Community Organization Guide were presented to PRAES Print Office for their review and recommendations.
* We continue working on Crops for High Tunnel Guide that will be include on High Tunnel Management and Production Guide
* Puerto Rico South West Earthquake and COVID- 19 cause a delay on project planning work
 |
| 1. Describe the work that you anticipate completing in the next six month
* Print and present training of Community Gardens Curriculum, Urban Agriculture Tool Kit, Agricultural Community Organization Guide and High Tunnel Management and Production Guide
 |