Cooperative Agreement

Quarterly Progress Report

04/01/2021-06/30/2021

| Grantee Name: Puerto Rico Agriculture Extension Service (PRAES) |  |
| --- | --- |
| Project Title: Urban Agriculture and Small High Tunnel Outreach Program (PAU) |  |
| Agreement Number: 68-F352-17-182 |  |
| Project Director: Dr. Myrna Comas myrna.comas@upr.edu | Phone (787)613-0134 |
| Contact Person Information: Roberto Rigau robertoluis.rigaullorens@upr.edu | Phone (787)765-8000 |
| Period Cover by Report: 04/01/2021-06/30/2021 |  |
| Project End Date: August 1, 2021 |  |
| General Progress Report - Staff and assistance student meeting to follow up project works. - PRAES Educative Office finish edition and design of five lessons of High Tunnel Management and Production Guide. - High Tunnel selection, installation, and management - Soil management for high tunnel system - Crops for high tunnel system - Pets and diseases control for crops in high tunnel system - Record keeping for high tunnel system. - PAU Staff and assistance students finish project videos recording. - NRCS High Tunnel Practices - Business Plan - Crops for high tunnel - Pest Management - Community gardens - CHEFS: Marketing Network Establishment Memories draft is on PRAES Educative Office for edition - Dr. Comas present “Planificando mi finca” and Guía para el agroempresario: Plan para el Establecimiento y Desarrollo de la Empresa Agrícola” training to 83 farmers May 26 2021. - Dr. Comas promote PAU and NRCS program mainly high tunnel conservation practice to Community Organization (Luis Colón coordinator) in Lajas, April 12, 2021. These are community organization with community gardens. - Dr. Comas promote PAU and NRCS program mainly high tunnel conservation practice between farmers. |  |
| Comparison of Actual and Proposed Accomplishments - We continue working on High Tunnel Management and Production Guide - We continue working on projects videos story board and recording. - Agriculture Community Organization - We continue working on projects videos edition. - Community Gardens - Business Plan - High Tunnel Construction - Soil Management - Crops for high tunnel - Pest Management |  |
| Describe the work that you anticipate completing in the next six months - Finish High Tunnel Management and Production Guide - Present High Tunnel Management and Production Guide training to PRAES personnel - Finish CHEFS: Marketing Network Establishment Memories - Finish Educative Video: - Community Gardens - Agriculture Community Organization - Business Plan - High Tunnel Construction - Soil Management - Crops for high tunnel - Pest Management - Continue promoting NRCS programs mainly high tunnel conservation practice. - Continue HT farmers visits and outreach. |  |